## Sheet1
Step | Input | Potential Failure Mode | Potential Failure Effects | Potential Causes | Current Control | Actions Recommended | Actions Taken
Making dual widgets | HIPS | Size is too small | Could slip off the clamp | Use of wrong unit of measurement/ untrained material cutter | Sketch out the measurement before cutting | Measure twice - before and after cutting | Cut another piece using the control method and the recommended action
|  | Size is too big | Will not fit within the clamp | Use of wrong unit of measurement/ untrained material cutter | Sketch out the measurement before cutting | Measure twice - before and after cutting | Cut out the excess by sketching out the region to be cut
| Hookup of the Thermoformer | Platen not rising to reach the HIPS | No parts were made | Loose wires on the limit switch | None | Check to see if all the wires are connected properly before starting the operation | Used a multimeter and followed the wires to see if the connections were secure
|  |  |  | Platen not levelled | Visual inspection | Adjust the levelling nuts on the bottom of the platen until the platen is at the preferred height | Raised the platen until we got it to the height we wanted
| Molds | Two molds close to each other | Bridging between the two parts and creases on the sides | Not enough space between molds for the material to form around | Left adequate space in between the two molds | Leave around 5.5 inches in between the molds | Increased the distance between the molds
|  | Nothing to cover the vaccum in between the two molds | Terrible definitions on the side | Giant hole in the middle of the sheet which prevented the suction to get to the molds | Placed scrap HIPS to cover the vacuum hole | Cover the hole with scarp HIPS | Placed scrap HIPS to cover the vacuum hole
|  | No platform under the molds | Very low quality widget formation | Not raising the mold constricts the airflow | None | Place a layer of HIPS underneath the mold | Used scrap HIPS to put under the mold
|  | No hole in the platform under the mold | Blurry definitions on the widget with creases on the sides | Platform covering the holes of the mold prevnting the airflow | Cut a hole on the HIPS platform adjacent to the holes in the mold | Cut a hole on the HIPS platform adjacent to the holes in the mold | Cut a hole on the HIPS platform adjacent to the holes in the mold
Quality Control Measurement | Measurers | Too many measurers | Increase in the inaccuracy of measurement | Variations in measurement | Use one person for measurement | Use one person for measurement | Use one person for measurement